## Pipeline Tracker
DATA PIPELINE PROJECT TRACKER
Stage | Sub-Task | Description | Owner | Status | Priority | Start Date | Due Date | % Complete | Dependencies | Deliverable | Notes / Risks
1. Data | Data Source Identification | Identify all candidate data sources (internal, vendor, public) |  | Not Started | High |  |  | 0% |  | Source inventory list
1. Data | Legal vs Not-Legal Assessment | Classify each source: permissible use, licensing, PII constraints |  | Not Started | High |  |  | 0% |  | Legal clearance matrix | Engage Legal/Compliance early
1. Data | Date Range Definition | Define observation window, backfill periods, and vintage dates |  | Not Started | High |  |  | 0% |  | Date range spec doc | Align with benchmark calendar
1. Data | Data Ingestion & Storage | Load raw data into staging environment; validate schema |  | Not Started | Medium |  |  | 0% |  | Staged dataset
2. Sampling | Simple vs Panel Decision | Decide sampling methodology — cross-sectional (simple) or longitudinal (panel) |  | Not Started | High |  |  | 0% | Data stage complete | Sampling design memo
2. Sampling | Sample Size Calculation | Power analysis / minimum sample thresholds per stratum |  | Not Started | High |  |  | 0% |  | Sample size table
2. Sampling | Panel Construction | If panel: define entity IDs, entry/exit rules, rebalance frequency |  | Not Started | Medium |  |  | 0% | Simple vs Panel decided | Panel spec document | Survivorship bias check
2. Sampling | Sampling Validation | Verify representativeness; compare sample vs population distributions |  | Not Started | Medium |  |  | 0% |  | Validation report
3. Inclusion Criteria | Floor & Ceiling Filters | Set min/max thresholds (AUM, market cap, revenue, etc.) |  | Not Started | High |  |  | 0% | Sampling complete | Filter rule set | Document rationale for each cutoff
3. Inclusion Criteria | Essentials Screen | Define must-have attributes (coverage, history length, quality score) |  | Not Started | High |  |  | 0% |  | Essentials checklist
3. Inclusion Criteria | Super Panel / Panel Classification | Tier entities into Super Panel (highest quality) vs standard Panel |  | Not Started | Medium |  |  | 0% |  | Tiered entity list
3. Inclusion Criteria | Min / Max / Mean / Median Analysis | Compute summary stats on filtered universe; flag outliers |  | Not Started | Medium |  |  | 0% |  | Summary stats table
4. EDA | Strata Analysis | Segment data by key dimensions (sector, geography, size band) |  | Not Started | High |  |  | 0% | Inclusion criteria finalized | Strata distribution charts
4. EDA | Survey / Jobs / Macro Data Review | Cross-reference with external survey, employment, or macro datasets |  | Not Started | Medium |  |  | 0% |  | Cross-reference summary
4. EDA | Time Series Exploration | Analyze trends, seasonality, structural breaks across the panel |  | Not Started | High |  |  | 0% |  | Time series plots & stats | Check for non-stationarity
4. EDA | Missing Data & Outlier Treatment | Imputation strategy, winsorization, or exclusion rules |  | Not Started | Medium |  |  | 0% |  | Data quality report
5. Benchmarks | SPICE / Custom Benchmark Design | Select or construct benchmark (index, peer group, composite) |  | Not Started | High |  |  | 0% | EDA complete | Benchmark definition doc | Clarify SPICE methodology
5. Benchmarks | Sort-Based Analysis | Rank entities by key metric; form quintiles/deciles |  | Not Started | Medium |  |  | 0% |  | Sort tables & spread analysis
5. Benchmarks | Correlation Analysis | Compute cross-sectional and time-series correlations |  | Not Started | Medium |  |  | 0% |  | Correlation matrix / heatmaps
5. Benchmarks | Other Benchmark Comparisons | Compare against additional external or internal benchmarks |  | Not Started | Low |  |  | 0% |  | Comparison tables
6. Reporting | Index Construction | Build reportable index from benchmarked data; define methodology |  | Not Started | High |  |  | 0% | Benchmarks complete | Index methodology doc
6. Reporting | Draft Report | Author narrative report with findings, charts, and recommendations |  | Not Started | High |  |  | 0% |  | Draft report (Word/PDF)
6. Reporting | Comparison / Attribution | Performance attribution vs benchmark; relative analysis |  | Not Started | Medium |  |  | 0% |  | Attribution tables
6. Reporting | Insights & Commentary | Executive-level insights, forward-looking implications |  | Not Started | High |  |  | 0% |  | Insights one-pager
7. Sign-Off | Internal Review | Circulate draft to stakeholders for review and feedback |  | Not Started | High |  |  | 0% | Draft report complete | Review comments log
7. Sign-Off | Final Approval & Distribution | Obtain sign-off; publish or distribute final deliverable |  | Not Started | High |  |  | 0% | Internal review complete | Signed-off final report
OVERALL PROGRESS | [7 empty] | 0%

## Stage Summary
STAGE SUMMARY DASHBOARD
Stage | Total Tasks | Not Started | In Progress | Complete | Blocked | Completion %
1. Data | 4 | 4 | 0 | 0 | 0 | 0%
2. Sampling | 4 | 4 | 0 | 0 | 0 | 0%
3. Inclusion Criteria | 4 | 4 | 0 | 0 | 0 | 0%
4. EDA | 4 | 4 | 0 | 0 | 0 | 0%
5. Benchmarks | 4 | 4 | 0 | 0 | 0 | 0%
6. Reporting | 4 | 4 | 0 | 0 | 0 | 0%
7. Sign-Off | 2 | 2 | 0 | 0 | 0 | 0%
TOTAL | 26 | 26 | 0 | 0 | 0 | 0%

## RACI Matrix
RACI RESPONSIBILITY MATRIX
Stage | Sub-Task | Data Eng | Data Science | Quant / Research | Legal / Compliance | Product Owner | Exec Sponsor
1. Data | Data Source Identification
1. Data | Legal vs Not-Legal Assessment
1. Data | Date Range Definition
1. Data | Data Ingestion & Storage
2. Sampling | Simple vs Panel Decision
2. Sampling | Sample Size Calculation
2. Sampling | Panel Construction
2. Sampling | Sampling Validation
3. Inclusion Criteria | Floor & Ceiling Filters
3. Inclusion Criteria | Essentials Screen
3. Inclusion Criteria | Super Panel / Panel Classification
3. Inclusion Criteria | Min / Max / Mean / Median Analysis
4. EDA | Strata Analysis
4. EDA | Survey / Jobs / Macro Data Review
4. EDA | Time Series Exploration
4. EDA | Missing Data & Outlier Treatment
5. Benchmarks | SPICE / Custom Benchmark Design
5. Benchmarks | Sort-Based Analysis
5. Benchmarks | Correlation Analysis
5. Benchmarks | Other Benchmark Comparisons
6. Reporting | Index Construction
6. Reporting | Draft Report
6. Reporting | Comparison / Attribution
6. Reporting | Insights & Commentary
7. Sign-Off | Internal Review
7. Sign-Off | Final Approval & Distribution

## Risk Log
RISK & ISSUE LOG
Risk ID | Related Stage | Risk Description | Likelihood | Impact | Risk Score | Mitigation Plan | Owner
R-001 | 1. Data | Data sources may have unresolved licensing/PII issues | Medium | High | High | Engage Legal in week 1; maintain clearance matrix
R-002 | 2. Sampling | Survivorship bias in panel construction | High | High | Critical | Backtest panel entry/exit rules against full history
R-003 | 3. Inclusion Criteria | Arbitrary floor/ceiling cutoffs bias results | Medium | Medium | Medium | Document rationale; run sensitivity analysis on cutoffs
R-004 | 4. EDA | Non-stationarity in time series invalidates analysis | Medium | High | High | Apply unit root tests; use differenced series if needed
R-005 | 5. Benchmarks | SPICE benchmark methodology unclear or contested | High | High | Critical | Define methodology doc; get stakeholder buy-in early
R-006 | 6. Reporting | Report findings misinterpreted without proper context | Low | High | High | Include methodology appendix; executive summary upfront